## Summary
| Total no. of positive test case | Total no. of negative test case | total TC's | Total no. of executed Positive test case | Total no of Negative TC executed | Total no of TC executed | Remaining Test cases to execute | Remarks
UI | 34 | 18 | 52 | 34 | 15 | 49 | 3 | - 3 Negative UI TCs can't be tested as we dont have option to give Invalid and Empty Value for Encryption Type
API | 18 | 12 | 30 | 18 | 12 | 30 | 0
Total | 52 | 30 | 82 | 52 | 27 | 79 | 3
| Total no. of positive test case | Total no. of negative test case | total TC's | Total no. of executed Positive test case | Total no of Negative TC executed | Total no of TC executed | Remaining Test cases to execute | Remarks
NRT UI | 34 | 18 | 52 | 34 | 15 | 49 | 3 | - 3 Negative UI TCs can't be tested as we dont have option to give Invalid and Empty Value for Encryption Type

## FirstDraft_TestScenarios
Positive Scenarios
Scenario Id | Test Scenario | Comment
AWS-GitHub-001 | Verify configuration of GitHub connector to the aws AppFabric
AWS-GitHub-002 | Verify that User should be able to create app bundle
AWS-GitHub-003 | Verify that user can create app bundle either through AWS owned
AWS-GitHub-004 | Verify that User should be able to authorize GitHub connector app in the form of ClientID, client secret, tenant id and tenant name.
AWS-GitHub-005 | Verify that user should be able to see the status of authorized GitHub app through AppFabric UI.
AWS-GitHub-006 | Verify that User should be able to configure GitHub connector for ingestion of audit logs
AWS-GitHub-007 | Verify that ingestion destination is created successfully for Amazon S3 bucket
AWS-GitHub-008 | Verify ingestion destination for each schema and format types i.e. OCSF-JSON for Identity and Normalization
AWS-GitHub-009 | Verify that ingestion destination is created successfully for Amazon Kinesis data Firehose
AWS-GitHub-010 | Verify tags for authorization and ingestion
AWS-GitHub-011 | Verify the status of ingestion and ingestion destination
AWS-GitHub-012 | Verify VTL mapping for user logs, user access and audit logs
AWS-GitHub-015 | Verify event logs of GitHub connector for different types of event like workspace_user_added group_user_added
AWS-GitHub-016 | Verify logs are being ingested correctly in the respective destination and types
AWS-GitHub-017 | Verify that user should be able to configure more than one GitHub connector
AWS-GitHub-018 | Verify that user should be able to see the connection details for GitHub connector
AWS-GitHub-019 | Verify the generated actions for the ISV are appearing in the logs and also check that no extraneous system actions are occurring
AWS-GitHub-020 | Verify user email address is being normalized and is appearing in the logs.
AWS-GitHub-021 | Verify that user should be able to edit the ingestion of authorized GitHub app through AppFabric UI
AWS-GitHub-022 | Verify that user should be able to disable the ingestion of authorized GitHub app through AppFabric UI
AWS-GitHub-023 | Verify that user should be able to add multiple destination for ingestion through AppFabric UI.
AWS-GitHub-024 | Verify that user should be able to see the logs in destination path.
AWS-GitHub-025 | Verify all the fields of logs i.e. owner, AWS region, Last modified, size, type, key, S3 URL, ARN, Entity Tag and Object URL.
AWS-GitHub-026 | Verify that user should be able to see all the connected app for a particular user by providing user email address through AppFabric UI.
AWS-GitHub-027 | Verify that user should be able to create app bundle using CreateAppBundle API.
AWS-GitHub-029 | Verify that user should be able to connect to the authorized GitHub app using ConnectAppAuthorization API.
AWS-GitHub-030 | Verify that user should be able to create ingestion using CreateIngestion API.
AWS-GitHub-031 | Verify that user should be able to add destination for ingestion of logs using CreateIngestionDestination API
AWS-GitHub-032 | Verify that user should be able delete app bundle using DeleteAppBundle API
AWS-GitHub-033 | Verify that user should be able to delete app authorization using DeleteAppAuthorization API
AWS-GitHub-034 | Verify that user should be able delete ingestion using DeleteIngestion API
AWS-GitHub-035 | Verify that user should be able to delete destination using DeleteIngestionDestination API
AWS-GitHub-036 | Verify that user should be able to update app authorization using UpdateAppAuthorization API
AWS-GitHub-037 | Verify that user should be able to update ingestion destination using UpdateIngestionDestination API
AWS-GitHub-038 | Verify that user should be able to start ingestion using StartIngestion API
AWS-GitHub-039 | Verify that user should be able to stop ingestion using StopIngestion API
AWS-GitHub-040 | Verify that user should be able to see user access using StartUserAccessTasks API
AWS-GitHub-041 | Verify that user should be able to add multiple destination using CreateIngestionDestination API
AWS-GitHub-042 | Verify that user should be able to create multiple app authorization for GitHub using CreateAppAuthorization API.
Negative Scenarios
AWS-GitHub-043 | I should get valid error message for invalid value of tenant id
AWS-GitHub-044 | I should get valid error message for invalid value of tenant name
AWS-GitHub-045 | I should get valid error message for invalid path of Amazon S3 bucket
AWS-GitHub-046 | I should get valid error message for invalid value of user email address for user access.
AWS-GitHub-047 | I should get valid error message, if user does not have permission.
AWS-GitHub-048 | I should get valid error message for ingestion if client secret is changed after creating app authorization
AWS-GitHub-049 | Verify that App autorization fails when incorrect value of Client Id or sceret is passed.
AWS-GitHub-050 | Verify that user should get valid error message for ingestion if password is changed after app authorization.
AWS-GitHub-051 | Verify that user should get valid error message for invalid value of instance URL
AWS-GitHub-052 | Verify that API should throw AccessDeniedException with error code 403 if user does not have sufficient access to perform the action
AWS-GitHub-053 | Verify that API should throw ExpiredTokenException with error code 403 if security token included in the request is expired
AWS-GitHub-054 | Verify that API should throw IncompleteSignature with error code 403 if request signature does not conform to AWS standards.
AWS-GitHub-055 | Verify that API should throw InternalFailure with error code 500 if request processing is failed because of an unknown error, exception or failure
AWS-GitHub-056 | Verify that API should throw MalformedHttpRequestException with error code 400 if there is a problem with the request at the HTTP level
AWS-GitHub-057 | Verify that API should throw NotAuthorized exception with error code 401 if user does not have permission to perform the action
AWS-GitHub-058 | Verify that API should throw OptInRequired exception with error code 403 if the AWS access key ID needs a subscription for the service.
AWS-GitHub-059 | Verify that API should throw RequestAbortedException with error code 400 when request is aborted before a reply is sent back (e.g. client closed connection).
AWS-GitHub-060 | Verify that API should throw RequestEntityTooLargeException with error code 413 if the request entity is too large.
AWS-GitHub-061 | Verify that API should throw RequestExpired exception with error code 400 if request reached the service more than 15 minutes after the date stamp on the request or more than 15 minutes after the request expiration date
AWS-GitHub-062 | Verify that API should throw RequestTimeoutException with error code 408 if request at the HTTP level timed out.
AWS-GitHub-063 | Verify that API should throw ServiceUnavailable exception with error code 503 if the request is failed due to a temporary failure of the server.
AWS-GitHub-064 | Verify that API should throw ThrottlingException with error code 400 if the request was denied due to request throttling.
AWS-GitHub-065 | Verify that API should throw UnrecognizedClientException with error code 403 if the AWS access key ID provided does not exist in our records
AWS-GitHub-066 | Verify that API should throw UnknownOperationException with error code 404 if the action or operation requested is invalid.
AWS-GitHub-067 | Verify that API should throw ValidationError with error code 400 if input fails to satisfy the constraints specified by an AWS service.

## API_TC
Positive Scenario
Test Scenario Id | Test_Case Id | Test Case Name | Test Case Description | Test Step # | Test Step Description | Expected Result | Actual Result | Pass/Fail | Test Data | Priority | Test Type | Automated | Author | Executed By | Executed on | Comments | Internal Defect ID | External Defect ID | Test Case Type
AWS-GitHub-001 | AWS-GitHub-TC-001 | Verify that user should be able to create app bundle using CreateAppBundle API. | Verify that user should be able to create app bundle using CreateAppBundle API. | 1 | Utilize postman and use CreateAppBundle API. | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | App bundle should be created successfully
AWS-GitHub-002 | AWS-GitHub-TC-002 | Verify that user should be able to connect to the authorized GitHub app using ConnectAppAuthorization API. | Verify that user should be able to connect to the authorized GitHub app using ConnectAppAuthorization API. | 1 | Utilize postman and use ConnectAppAuthorization API. | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | App authroization should be created successfully
AWS-GitHub-003 | AWS-GitHub-TC-003 | Verify that user should be able to create ingestion using CreateIngestion API. | Verify that user should be able to create ingestion using CreateIngestion API. | 1 | Utilize postman and use CreateIngestion API. | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Ingestion should be created successfully
AWS-GitHub-003 | AWS-GitHub-TC-004 | Verify that user should be able to add destination for ingestion of logs using CreateIngestionDestination API | Verify that user should be able to add destination for ingestion of logs using CreateIngestionDestination API | 1 | Utilize postman and use CreateIngestionDestination API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Ingestion destinationshould be created successfully
AWS-GitHub-004 | AWS-GitHub-TC-005 | Verify that user should be able delete app bundle using DeleteAppBundle API | Verify that user should be able delete app bundle using DeleteAppBundle API | 1 | Utilize postman and use DeleteAppBundle API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Bundle should be deleted successfully
AWS-GitHub-005 | AWS-GitHub-TC-006 | Verify that user should be able to delete app authorization using DeleteAppAuthorization API | Verify that user should be able to delete app authorization using DeleteAppAuthorization API | 1 | Utilize postman and use DeleteAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | App authorization should be deleted successfully
AWS-GitHub-006 | AWS-GitHub-TC-007 | Verify that user should be able delete ingestion using DeleteIngestion API | Verify that user should be able delete ingestion using DeleteIngestion API | 1 | Utilize postman and use DeleteIngestion API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Ingestion should be deleted successfully
AWS-GitHub-007 | AWS-GitHub-TC-008 | Verify that user should be able to delete destination using DeleteIngestionDestination API | Verify that user should be able to delete destination using DeleteIngestionDestination API | 1 | Utilize postman and use DeleteIngestionDestination API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Ingestion destination should be deleted successfully
AWS-GitHub-008 | AWS-GitHub-TC-009 | Verify that user should be able to update app authorization using UpdateAppAuthorization API | Verify that user should be able to update app authorization using UpdateAppAuthorization API | 1 | Utilize postman and use UpdateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | App Authorization should be updated successfully
AWS-GitHub-09 | AWS-GitHub-TC-010 | Verify that user should be able to update ingestion destination using UpdateIngestionDestination API | Verify that user should be able to update ingestion destination using UpdateIngestionDestination API | 1 | Utilize postman and use UpdateIngestionDestination API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Ingestion destination should be updated successfully
AWS-GitHub-010 | AWS-GitHub-TC-011 | Verify that user should be able to start ingestion using StartIngestion API | Verify that user should be able to start ingestion using StartIngestion API | 1 | Utilize postman and use StartIngestion API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Ingestion should be started successfully
AWS-GitHub-011 | AWS-GitHub-TC-012 | Verify that user should be able to stop ingestion using StopIngestion API | Verify that user should be able to stop ingestion using StopIngestion API | 1 | Utilize postman and use StopIngestion API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Ingestion should be stopped successfully
AWS-GitHub-013 | AWS-GitHub-TC-014 | Verify that user should be able to add multiple destination using CreateIngestionDestination API | Verify that user should be able to add multiple destination using CreateIngestionDestination API | 1 | Utilize postman and use CreateIngestionDestination API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Multiple ingestion destination should be created successfully
AWS-GitHub-013 | AWS-GitHub-TC-015 | Verify that user should be able to create multiple app authorization for GitHub using CreateAppAuthorization API. | Verify that user should be able to create multiple app authorization for GitHub using CreateAppAuthorization API. | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No | [6 empty] | API Test Case
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Multiple app authorization should be created successfully
AWS-GitHub-014 | AWS-GitHub-TC-016 | Verify that user should be able to get Audit Logs using GetAuditLogs API from GitHub | Verify that user should be able to get Audit Logs using GetAuditLogs API from GitHub | 1 | Utilize postman and use GetAuditLogs API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | Audit Log records should get successfully
AWS-GitHub-016 | AWS-GitHub-TC-017 | Verify that user should be able to get users using GetUser API from GitHub | Verify that user should be able to get users using GetUser API from GitHub | 1 | Utilize postman and use GetUser API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | User records should get successfully
AWS-GitHub-017 | AWS-GitHub-TC-018 | Verify that user should be able to find user access using StartUserAccess API from GitHub | Verify that user should be able to find user access using StartUserAccess API from GitHub | 1 | Utilize postman and use StartUserAccess API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | User Access records should get successfully
AWS-GitHub-018 | AWS-GitHub-TC-019 | Verify that user should be able to find user access using BatchGetUserAccess API from GitHub | Verify that user should be able to find user access using BatchGetUserAccess API from GitHub | 1 | Utilize postman and use BatchGetUserAccess API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide the POST body required for the query. | required POST body should be provided with correct entity-name
|  |  |  | 3 | Set correct AWS Authorization access information in postman | AWS authorization should be provided
|  |  |  | 4 | Trigger the query using run button | User Access Results List records should get successfully
Negative Scenario
AWS_GitHub_API_001 | AWS-GitHub-TC-020 | Verify that API should throw valid error message for invalid value of client id while creating app authorization | Verify that API should throw valid error message for invalid value of client id while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide invalid values to client id | required POST body should be provided with incorrect values of client id.
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_002 | AWS-GitHub-TC-021 | Verify that API should throw valid error message for empty value of client id while creating app authorization | Verify that API should throw valid error message for empty value of client id while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide empty values to client id | required POST body should be provided with empty values of client id.
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_003 | AWS-GitHub-TC-022 | Verify that API should throw valid error message for invalid value of client secret while creating app authorization | Verify that API should throw valid error message for invalid value of client secret while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide invalid values to client secret | required POST body should be provided with incorrect values of client secret.
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_004 | AWS-GitHub-TC-023 | Verify that API should throw valid error message for empty value of client secret while creating app authorization | Verify that API should throw valid error message for empty value of client secret while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide empty values to client secret | required POST body should be provided with empty values of client secret.
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_005 | AWS-GitHub-TC-024 | Verify that API should throw valid error message for invalid value of tenant id while creating app authorization | Verify that API should throw valid error message for invalid value of tenant id while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide invalid values to tenant id | required POST body should be provided with incorrect values of tenant id.
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_006 | AWS-GitHub-TC-025 | Verify that API should throw valid error message for empty value of tenant id while creating app authorization | Verify that API should throw valid error message for empty value of tenant id while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide empty values to tenant id | required POST body should be provided with empty values of tenant id
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_007 | AWS-GitHub-TC-026 | Verify that API should throw valid error message for invalid value of tenant name while creating app authorization | Verify that API should throw valid error message for invalid value of tenant name while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide invalid values to tenant name | required POST body should be provided with incorrect values of tenant name.
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_008 | AWS-GitHub-TC-027 | Verify that API should throw valid error message for empty value of tenant name while creating app authorization | Verify that API should throw valid error message for empty value of tenant name while creating app authorization. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateAppAuthorization API | Postman should be open and request given should be activated |  | Pass |  | P1 | Positive | No
|  |  |  | 2 | Provide empty values to tenant name | required POST body should be provided with empty values of tenant name
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_009 | AWS-GitHub-TC-028 | Verify that API should throw valid error message for invalid destination path | Verify that API should throw valid error message for invalid destination path Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use CreateIngestiondestination API | Postman should be open and request given should be activated |  | Pass
|  |  |  | 2 | Provide invalid values of destination path | required POST body should be provided with invalid values of destination path
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_010 | AWS-GitHub-TC-029 | Verify that API should throw valid error message for creating ingestion if App is not connected | Verify that API should throw valid error message for creating ingestion if App is not connected Pre Condition: 1. User should have aws credentials 2. App should not be connected | 1 | Utilize postman and use CreateIngestion API | Postman should be open and request given should be activated |  | Pass
|  |  |  | 2 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_010 | AWS-GitHub-TC-030 | Verify that API should throw valid error message for invalid value of user email address to check user access. | Verify that API should throw valid error message for invalid value of user email address to check user access. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use StartUserAccessTasks API | Postman should be open and request given should be activated |  | Pass
|  |  |  | 2 | Provide invalid values of user email address | required POST body should be provided with invalid values of user email address
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message
AWS_GitHub_API_012 | AWS-GitHub-TC-031 | Verify that API should throw valid error message for empty value of user email address to check user access. | Verify that API should throw valid error message for empty value of user email address to check user access. Pre Condition: 1. User should have aws credentials | 1 | Utilize postman and use StartUserAccessTasks API | Postman should be open and request given should be activated |  | Pass
|  |  |  | 2 | Provide empty values of user email address | required POST body should be provided with empty values of user email address
|  |  |  | 3 | Trigger the query using run button | API should throw valid error message

## UI_NRT_TC's
Positive Scenario
Test Scenario Id | Test_Case Id | Test Case Name | Test Case Description | Test Step # | Test Step Description | Expected Result | Actual Result | Pass/Fail | Test Data | Priority | Test Type | Automated | Author | Executed By | Executed on | Comments | Internal Defect ID | External Defect ID | Test Case Type
AWS_GitHub_UI_001 | AWS-GitHub-TC-001 | Verify that user should be able to configure GitHub connector to the aws AppFabric | Verify that user should be able to configure GitHub connector to the aws AppFabric Pre Condition: Login to Amazon AWS AppFabric account. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Create AppBundle | User should be able to create app bundle
|  |  |  | 3 | Create AppAuthorization for GitHub app | GitHub app should be available for app authorization and user should be able to authorize GitHub app
AWS_GitHub_UI_002 | AWS-GitHub-TC-002 | Verify that user should be able to create app bundle through AppFabric UI and should provide encryption, AWS KMS Key and Tags. | Verify that user should be able to create app bundle through AppFabric UI and should provide encryption, AWS KMS Key and Tags. Pre Condition: Login to Amazon AWS AppFabric Account. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to click on App Bundle
|  |  |  | 3 | Provide all the required fields like encryption, AWS KMS Key and Tags and click on submit | User should be able to provide all the required details and should be able to create AppBundle after clicking on submit.
AWS_GitHub_UI_003 | AWS-GitHub-TC-003 | Verify that user should be able to delete app bundle through AppFabric UI | Verify that user should be able to delete app bundle through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to inquire App Bundle details
|  |  |  | 3 | Click on Delete | After clicking on delete, User should be able to delete App Bundle.
AWS_GitHub_UI_004 | AWS-GitHub-TC-004 | Verify that user should be able to authorize GitHub App through AppFabric UI. | Verify that user should be able to authorize GitHub App through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on Create App Authorization | User should be able to click on create App Authorization
|  |  |  | 4 | Select GitHub Application and fill all the required details details like tenant id, tenant name, Client Id, Client secret. | GitHub Application should be available and user should be able to fill all the required details.
|  |  |  | 5 | Click on Create App Authorization | User should be able to create app authorization for GitHub application
AWS_GitHub_UI_005 | AWS-GitHub-TC-005 | Verify that user should be able to connect to the authorized GitHub app through AppFabric UI. | Verify that user should be able to connect to the authorized GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Connect | User should be able to connect to GitHub App.
AWS_GitHub_UI_006 | AWS-GitHub-TC-006 | Verify that user should be able to see the status of authorized GitHub app through AppFabric UI. | Verify that user should be able to see the status of authorized GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | See status | User should be able to see the status of GitHub app. It shoule be in connected status.
AWS_GitHub_UI_007 | AWS-GitHub-TC-007 | Verify that user should be able to update credentials of GitHub app through AppFabric UI. | Verify that user should be able to update credentials of GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Update Creadentials | User should be able to update credenatials of GitHub app.
AWS_GitHub_UI_008 | AWS-GitHub-TC-008 | Verify that user should be able to edit GitHub app through AppFabric UI. | Verify that user should be able to edit GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Edit | User should be able to edit GitHub app.
AWS_GitHub_UI_009 | AWS-GitHub-TC-009 | Verify that user should be able to delete GitHub app through AppFabric UI. | Verify that user should be able to delete GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Delete | User should be able to delete GitHub app.
AWS_GitHub_UI_010 | AWS-GitHub-TC-010 | Verify that user should be able to create ingestion for authorized GitHub app through AppFabric UI. | Verify that user should be able to create ingestion for authorized GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to click on ingestions
|  |  |  | 3 | Click on Create Ingestion and provide the details | User should be able to create ingestion after providing all the details
AWS_GitHub_UI_011 | AWS-GitHub-TC-011 | Verify that user should be able to add destination for ingestion of logs through AppFabric UI. | Verify that user should be able to add destination for ingestion of logs through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to click on ingestions
|  |  |  | 3 | Click on Add Destination | User should be able to add Destination for ingestions to store audit logs.
AWS_GitHub_UI_012 | AWS-GitHub-TC-012 | Verify that user should be able to create Amazon S3 bucket to store logs through AppFabric UI. | Verify that user should be able to create Amazon S3 bucket to store logs through AppFabric UI. Pre Condition: Login to Amazon AWS AppFabric Account. | 1 | Go to Amazon S3 | User should be able to navigate to Amazon S3 |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Create Bucket and provide details | User should be able to create bucket after providing all the required details.
AWS_GitHub_UI_013 | AWS-GitHub-TC-013 | Verify that user should be able to provide schema and format types as OCSF-JSON. | Verify that user should be able to provide schema and format types as OCSF-JSON. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and give schema and format types as OCSF-JSON. | User should be able to provide schema and format types as OCSF-JSON.
AWS_GitHub_UI_028 | AWS-GitHub-TC-014 | Verify that user should be able to provide schema and format types as OCSF-Parquet | Verify that user should be able to provide schema and format types as OCSF-Parquet Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and give schema and format types as OCSF-Parquet | User should be able to provide schema and format types as OCSF-Parquet
AWS_GitHub_UI_029 | AWS-GitHub-TC-015 | Verify that user should be able to provide schema and format types as Raw-JSON | Verify that user should be able to provide schema and format types as Raw-JSON Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and give schema and format types as Raw-JSON | User should be able to provide schema and format types as Raw-JSON
AWS_GitHub_UI_014 | AWS-GitHub-TC-016 | Verify that ingestion destination is created successfully for Amazon Kinesis data Firehose | Verify that ingestion destination is created successfully for Amazon Kinesis data Firehose Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and provide add Destination as Amazon Kinesis data Firehose | User should be able to provide Amazon Kinesis data Firehose in add destination. | Dont' have the permission to create Firhose destination. Getting error page not found
AWS_GitHub_UI_015 | AWS-GitHub-TC-017 | Verify that user should be able to add tags for authorizations. | Verify that user should be able to add tags for authorizations. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations and open GitHub app | User should be able to navigate to app authorizations
|  |  |  | 3 | Click on manage tags and add new tags | User should be able to add new tags for authorizations
AWS_GitHub_UI_015 | AWS-GitHub-TC-017 | Verify that user should be able to add tags for ingestions | Verify that user should be able to add tags for ingestions. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on manage tags and add new tags | User should be able to add new tags for ingestions
AWS_GitHub_UI_016 | AWS-GitHub-TC-018 | Verify that user should be able to see the status of ingestion | Verify that user should be able to see the status of ingestion Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | See status | Status should be Enabled
AWS_GitHub_UI_016 | AWS-GitHub-TC-019 | Verify that user should be able to see the status of ingestion destination | Verify that user should be able to see the status of ingestion destination Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | See status of destination | Status should be Active
AWS_GitHub_UI_033 | AWS-GitHub-TC-020 | Verify that user should be able to delete the ingestion of authorized GitHub app through AppFabric UI | Verify that user should be able to delete the ingestion of authorized GitHub app through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on delete | User should be able to delete the ingestion.
AWS_GitHub_UI_017 | AWS-GitHub-TC-021 | Verify that user should be able to disable ingestions of GitHub app through AppFabric UI | Verify that user should be able to disable ingestions of GitHub app through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on disable | User should be able to disable the ingestions
AWS_GitHub_UI_018 | AWS-GitHub-TC-022 | Verify that user should be able to add multiple destination for ingestion through AppFabric Ui. | Verify that user should be able to add multiple destination for ingestion through AppFabric Ui. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on Add Destination | User should be able to add multiple destinations
AWS_GitHub_UI_019 | AWS-GitHub-TC-023 | Verify that user should be able to see the logs in destination path. | Verify that user should be able to see the logs in destination path. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Go to Destination like S3 Bucket | User should be able to navigate to logs destination
|  |  |  | 3 | Verify logs | User should be able to verify logs in the destinations
AWS_GitHub_UI_034 | AWS-GitHub-TC-024 | Verify the fields of log through AppFabric UI. | Verify the fields of log through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Go to logs destinations | User should be able to navigate to logs destination
|  |  |  | 3 | Verify fields of logs i.e. owner, AWS region, Last modified, size, type, key, S3 URL, ARN, Entity Tag and Object url. | All fields value should be correct.
AWS_GitHub_UI_020 | AWS-GitHub-TC-025 | Verify that user should be able to see all the connected app for a particular user by providing user email address through AppFabric UI. | Verify that user should be able to see all the connected app for a particular user by providing user email address through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on user access | User should be able to navigate to user access
|  |  |  | 3 | Enter email address of user | After entering email address of user, user should be able to see all the connected app for the user
AWS_GitHub_UI_021 | AWS-GitHub-TC-026 | Verify the VTL mapping for user | Verify the VTL mapping for user | 1 | VTL mapping of user | VTL mapping for user should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_022 | AWS-GitHub-TC-027 | Verify the VTL mapping for user access | Verify the VTL mapping for user access | 1 | VTL mapping of user access | VTL mapping for user access should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_023 | AWS-GitHub-TC-028 | Verify the VTL mapping for audit logs | Verify the VTL mapping for audit logs | 1 | VTL mapping of audit logs | VTL mapping for audit logs should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_024 | AWS-GitHub-TC-029 | Verify the event logs for GitHub connector for different types of event like login, logout, file_donwloaded etc. | Verify the event logs for GitHub connector for different types of event like login, logout, file_downloaded etc. | 1 | Event logs for different types of event like login, logout, APiTotalUsage etc. | Event logs of GitHub connector should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_025 | AWS-GitHub-TC-030 | Verify logs are being ingested correctly in the respective destination and types | Verify logs are being ingested correctly in the respective destination and types through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestion | User should be able to navigate to ingestions
|  |  |  | 3 | Click on Add destination for for audit logs igestion and also add format | User should be able to add Destination for ingestions to store audit logs.
|  |  |  | 4 | Go to the destination and verify logs and format | Logs should ingest to the correct path with selected schema and format.
AWS_GitHub_UI_026 | AWS-GitHub-TC-031 | Verify that user should be able to configure more than one GitHub connector | Verify that user should be able to configure more than one GitHub connector through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on Create App Authorization and create mulitple app authorization for GitHub app | User should be able to create multiple app authorization for GitHub app.
AWS_GitHub_UI_027 | AWS-GitHub-TC-032 | Verify that user should be able to see the connection details for GitHub connector | Verify that user should be able to see the connection details for GitHub connector through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Verify the details of GitHub app | User should be able to verify the details of GitHub app.
AWS_GitHub_UI_031 | AWS-GitHub-TC-033 | Verify that user should be able to perform user access for multiple ISV | Verify that user should be able to perform user access for multiple ISV through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created for multiple ISV | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Create App authorization for multiple ISV | User should be able to create app authorization for multiple ISV.
|  |  |  | 3 | Verify User access | User should get details of app authorization for multiple ISV
AWS-GitHub_UI-032 | AWS-GitHub-TC-034 | Verify pagination for GitHub audit logs through UI | Verify pagination for GitHub audit logs through UI | 1 | Generate audit logs for more than 100 records | Audit log should be generated | Multiple audit log files generated with each file having maximum of 16 records | Pass
Negative Scenario
AWS_GitHub_UI_028 | AWS-GitHub-TC-036 | Verify that user should get valid error message for invalid value of encryption type while creating bundle | Verify that user should get valid error message for invalid value of encryption type while creating bundle. Pre Condition: 1. User should have aws credentials | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Can't be tested |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to click on App Bundle
|  |  |  | 3 | Provide invalid value to encryption type and click on submit | User should get valid error message for invalid value of encryption type | We dont have option to give Invalid and Empty Value for Encryption Type
AWS_GitHub_UI_028 | AWS-GitHub-TC-037 | Verify that user should get valid error message for empty value of encryption type while creating bundle | Verify that user should get valid error message for empty value of encryption type while creating bundle. Pre Condition: 1. User should have aws credentials | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Can't be tested |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to click on App Bundle
|  |  |  | 3 | Provide empty value to encryption type and click on submit | User should get valid error message for empty value of encryption type | We dont have option to give Invalid and Empty Value for Encryption Type
AWS_GitHub_UI_029 | AWS-GitHub-TC-038 | Verify that user should get valid error message for invalid value of client id | Verify that user should get valid error message for invalid value of client id through AppFabric UI. Pre Condition: Login to Amazon AWS AppFabric account. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client id and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of client id | User should get valid error message
AWS_GitHub_UI_029 | AWS-GitHub-TC-039 | Verify that user should get valid error message for empty value of client id | Verify that user should get valid error message for empty value of client id through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client id and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of client id | User should get valid error message
AWS_GitHub_UI_030 | AWS-GitHub-TC-040 | Verify that user should get valid error message for invalid value of client secret | Verify that user should get valid error message for invalid value of client secret through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client secret and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of client secret | User should get valid error message
AWS_GitHub_UI_030 | AWS-GitHub-TC-041 | Verify that user should get valid error message for empty value of client secret | Verify that user should get valid error message for empty value of client secret through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client secret and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of client secret | User should get valid error message
AWS_GitHub_UI_031 | AWS-GitHub-TC-042 | Verify that user should get valid error message for invalid value of tenant id | Verify that user should get valid error message for invalid value of tenant id through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of tenant id , Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of tenant id | User should get valid error message
AWS_GitHub_UI_031 | AWS-GitHub-TC-043 | Verify that user should get valid error message for empty value of tenant id | Verify that user should get valid error message for empty value of tenant id through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of tenant id , Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of tenant id | User should get valid error message
AWS_GitHub_UI_032 | AWS-GitHub-TC-044 | Verify that user should get valid error message for invalid value of tenant name | Verify that user should get valid error message for invalid value of tenant name through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric | We can give any value to tenant name. So can't test this for invalid value of tenant name | Can't be tested |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of tenant name | User should get valid error message
AWS_GitHub_UI_032 | AWS-GitHub-TC-045 | Verify that user should get valid error message for empty value of tenant name | Verify that user should get valid error message for empty value of tenant name through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of tenant name | User should get valid error message
AWS_GitHub_UI_033 | AWS-GitHub-TC-046 | Verify that user should get valid error message for invalid value of Amazon S3 path. | Verify that user should get valid error message for invalid value of Amazon S3 path through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of Amazon S3 path | User should get valid error message
AWS_GitHub_UI_034 | AWS-GitHub-TC-047 | Verify that user should get valid error message for empty value of destination | Verify that user should get valid error message for empty value of destination through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of destination | User should get valid error message
AWS_GitHub_UI_035 | AWS-GitHub-TC-048 | Verify that user should get valid error message for invalid value of user email address for user access | Verify that user should get valid error message for invalid value of user email address for user access through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on user access | User should be able to navigate to user access
|  |  |  | 3 | Provide invalid email address | User should get valid error message
AWS_GitHub_UI_036 | AWS-GitHub-TC-049 | Verify that user should get valid error message if user does not have permission for the action | Verify that user should get valid error message if user does not have permission for the action through AppFabric UI. | 1 | Login to AWS app fabric with user having less permission | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Try to perform any action which does not have access to the user | User should get valid error message
AWS_GitHub_UI_037 | AWS-GitHub-TC-050 | Verify that user should get valid error message for ingestion if client secret is expired after app authorization. | Verify that user should get valid error message for ingestion if client secret is expired after app authorization through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Token not expiring for Github Oauth apps |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Create App Authorization by providing valid client secret | User should be able to create app authorization for GitHub app.
|  |  |  | 4 | After client secret expiration, try to create another app authorization for GitHub app. | User should get valid error message
AWS_GitHub_UI_038 | AWS-GitHub-TC-051 | Verify that user should get valid error message for ingestion if password is changed after app authorization. | Verify that user should get valid error message for ingestion if password is changed after app authorization. through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Create App Authorization by providing valid client secret | User should be able to create app authorization for GitHub app.
|  |  |  | 4 | After client secret expiration, try to create another app authorization for GitHub app. | User should get valid error message
AWS_GitHub_UI_039 | AWS-GitHub-TC-052 | Verify that user should get valid error message for invalid value of instance url | Verify that user should get valid error message for invalid value of instance url through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Connect to GitHub app by providing invalid value of instance URL. | User should get valid error message
AWS_GitHub_UI_040 | AWS-GitHub-TC-052 | Verify that user should get valid error message for creating ingestion if app is not connected. | Verify that user should get valid error message for creating ingestion if app is not connected through App Fabric UI | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations and authorize GitHub app.
|  |  |  | 3 | Create ingestion without connecting to the app | User should get valid error message.

## UI_Gamma_TC's
Positive Scenario
Test Scenario Id | Test_Case Id | Test Case Name | Test Case Description | Test Step # | Test Step Description | Expected Result | Actual Result | Pass/Fail | Test Data | Priority | Test Type | Automated | Author | Executed By | Executed on | Comments | Internal Defect ID | External Defect ID | Test Case Type
AWS_GitHub_UI_001 | AWS-GitHub-TC-001 | Verify that user should be able to configure GitHub connector to the aws AppFabric | Verify that user should be able to configure GitHub connector to the aws AppFabric Pre Condition: Login to Amazon AWS AppFabric account. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Create AppBundle | User should be able to create app bundle
|  |  |  | 3 | Create AppAuthorization for GitHub app | GitHub app should be available for app authorization and user should be able to authorize GitHub app
AWS_GitHub_UI_002 | AWS-GitHub-TC-002 | Verify that user should be able to create app bundle through AppFabric UI and should provide encryption, AWS KMS Key and Tags. | Verify that user should be able to create app bundle through AppFabric UI and should provide encryption, AWS KMS Key and Tags. Pre Condition: Login to Amazon AWS AppFabric Account. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to click on App Bundle
|  |  |  | 3 | Provide all the required fields like encryption, AWS KMS Key and Tags and click on submit | User should be able to provide all the required details and should be able to create AppBundle after clicking on submit.
AWS_GitHub_UI_003 | AWS-GitHub-TC-003 | Verify that user should be able to delete app bundle through AppFabric UI | Verify that user should be able to delete app bundle through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to inquire App Bundle details
|  |  |  | 3 | Click on Delete | After clicking on delete, User should be able to delete App Bundle.
AWS_GitHub_UI_004 | AWS-GitHub-TC-004 | Verify that user should be able to authorize GitHub App through AppFabric UI. | Verify that user should be able to authorize GitHub App through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on Create App Authorization | User should be able to click on create App Authorization
|  |  |  | 4 | Select GitHub Application and fill all the required details details like tenant id, tenant name, Client Id, Client secret. | GitHub Application should be available and user should be able to fill all the required details.
|  |  |  | 5 | Click on Create App Authorization | User should be able to create app authorization for GitHub application
AWS_GitHub_UI_005 | AWS-GitHub-TC-005 | Verify that user should be able to connect to the authorized GitHub app through AppFabric UI. | Verify that user should be able to connect to the authorized GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Connect | User should be able to connect to GitHub App.
AWS_GitHub_UI_006 | AWS-GitHub-TC-006 | Verify that user should be able to see the status of authorized GitHub app through AppFabric UI. | Verify that user should be able to see the status of authorized GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | See status | User should be able to see the status of GitHub app. It shoule be in connected status.
AWS_GitHub_UI_007 | AWS-GitHub-TC-007 | Verify that user should be able to update credentials of GitHub app through AppFabric UI. | Verify that user should be able to update credentials of GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Update Creadentials | User should be able to update credenatials of GitHub app.
AWS_GitHub_UI_008 | AWS-GitHub-TC-008 | Verify that user should be able to edit GitHub app through AppFabric UI. | Verify that user should be able to edit GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Edit | User should be able to edit GitHub app.
AWS_GitHub_UI_009 | AWS-GitHub-TC-009 | Verify that user should be able to delete GitHub app through AppFabric UI. | Verify that user should be able to delete GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations | User should be able to inquire App Authorization details of GitHub app
|  |  |  | 3 | Click on Delete | User should be able to delete GitHub app.
AWS_GitHub_UI_010 | AWS-GitHub-TC-010 | Verify that user should be able to create ingestion for authorized GitHub app through AppFabric UI. | Verify that user should be able to create ingestion for authorized GitHub app through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App AUthorization should be create | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to click on ingestions
|  |  |  | 3 | Click on Create Ingestion and provide the details | User should be able to create ingestion after providing all the details
AWS_GitHub_UI_011 | AWS-GitHub-TC-011 | Verify that user should be able to add destination for ingestion of logs through AppFabric UI. | Verify that user should be able to add destination for ingestion of logs through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to click on ingestions
|  |  |  | 3 | Click on Add Destination | User should be able to add Destination for ingestions to store audit logs.
AWS_GitHub_UI_012 | AWS-GitHub-TC-012 | Verify that user should be able to create Amazon S3 bucket to store logs through AppFabric UI. | Verify that user should be able to create Amazon S3 bucket to store logs through AppFabric UI. Pre Condition: Login to Amazon AWS AppFabric Account. | 1 | Go to Amazon S3 | User should be able to navigate to Amazon S3 |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Create Bucket and provide details | User should be able to create bucket after providing all the required details.
AWS_GitHub_UI_013 | AWS-GitHub-TC-013 | Verify that user should be able to provide schema and format types as OCSF-JSON. | Verify that user should be able to provide schema and format types as OCSF-JSON. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and give schema and format types as OCSF-JSON. | User should be able to provide schema and format types as OCSF-JSON.
AWS_GitHub_UI_028 | AWS-GitHub-TC-014 | Verify that user should be able to provide schema and format types as OCSF-Parquet | Verify that user should be able to provide schema and format types as OCSF-Parquet Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and give schema and format types as OCSF-Parquet | User should be able to provide schema and format types as OCSF-Parquet
AWS_GitHub_UI_029 | AWS-GitHub-TC-015 | Verify that user should be able to provide schema and format types as Raw-JSON | Verify that user should be able to provide schema and format types as Raw-JSON Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and give schema and format types as Raw-JSON | User should be able to provide schema and format types as Raw-JSON
AWS_GitHub_UI_014 | AWS-GitHub-TC-016 | Verify that ingestion destination is created successfully for Amazon Kinesis data Firehose | Verify that ingestion destination is created successfully for Amazon Kinesis data Firehose Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on Ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on create ingestion and provide add Destination as Amazon Kinesis data Firehose | User should be able to provide Amazon Kinesis data Firehose in add destination. | Dont' have the permission to create Firhose destination. Getting error page not found
AWS_GitHub_UI_015 | AWS-GitHub-TC-017 | Verify that user should be able to add tags for authorizations. | Verify that user should be able to add tags for authorizations. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorizations and open GitHub app | User should be able to navigate to app authorizations
|  |  |  | 3 | Click on manage tags and add new tags | User should be able to add new tags for authorizations
AWS_GitHub_UI_015 | AWS-GitHub-TC-017 | Verify that user should be able to add tags for ingestions | Verify that user should be able to add tags for ingestions. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on manage tags and add new tags | User should be able to add new tags for ingestions
AWS_GitHub_UI_016 | AWS-GitHub-TC-018 | Verify that user should be able to see the status of ingestion | Verify that user should be able to see the status of ingestion Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | See status | Status should be Enabled
AWS_GitHub_UI_016 | AWS-GitHub-TC-019 | Verify that user should be able to see the status of ingestion destination | Verify that user should be able to see the status of ingestion destination Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | See status of destination | Status should be Active
AWS_GitHub_UI_033 | AWS-GitHub-TC-020 | Verify that user should be able to delete the ingestion of authorized GitHub app through AppFabric UI | Verify that user should be able to delete the ingestion of authorized GitHub app through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on delete | User should be able to delete the ingestion.
AWS_GitHub_UI_017 | AWS-GitHub-TC-021 | Verify that user should be able to disable ingestions of GitHub app through AppFabric UI | Verify that user should be able to disable ingestions of GitHub app through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on disable | User should be able to disable the ingestions
AWS_GitHub_UI_018 | AWS-GitHub-TC-022 | Verify that user should be able to add multiple destination for ingestion through AppFabric Ui. | Verify that user should be able to add multiple destination for ingestion through AppFabric Ui. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestions and open GitHub app ingestions | User should be able to navigate to ingestions
|  |  |  | 3 | Click on Add Destination | User should be able to add multiple destinations
AWS_GitHub_UI_019 | AWS-GitHub-TC-023 | Verify that user should be able to see the logs in destination path. | Verify that user should be able to see the logs in destination path. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Go to Destination like S3 Bucket | User should be able to navigate to logs destination
|  |  |  | 3 | Verify logs | User should be able to verify logs in the destinations
AWS_GitHub_UI_034 | AWS-GitHub-TC-024 | Verify the fields of log through AppFabric UI. | Verify the fields of log through AppFabric UI Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Go to logs destinations | User should be able to navigate to logs destination
|  |  |  | 3 | Verify fields of logs i.e. owner, AWS region, Last modified, size, type, key, S3 URL, ARN, Entity Tag and Object url. | All fields value should be correct.
AWS_GitHub_UI_020 | AWS-GitHub-TC-025 | Verify that user should be able to see all the connected app for a particular user by providing user email address through AppFabric UI. | Verify that user should be able to see all the connected app for a particular user by providing user email address through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on user access | User should be able to navigate to user access
|  |  |  | 3 | Enter email address of user | After entering email address of user, user should be able to see all the connected app for the user
AWS_GitHub_UI_021 | AWS-GitHub-TC-026 | Verify the VTL mapping for user | Verify the VTL mapping for user | 1 | VTL mapping of user | VTL mapping for user should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_022 | AWS-GitHub-TC-027 | Verify the VTL mapping for user access | Verify the VTL mapping for user access | 1 | VTL mapping of user access | VTL mapping for user access should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_023 | AWS-GitHub-TC-028 | Verify the VTL mapping for audit logs | Verify the VTL mapping for audit logs | 1 | VTL mapping of audit logs | VTL mapping for audit logs should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_024 | AWS-GitHub-TC-029 | Verify the event logs for GitHub connector for different types of event like login, logout, file_donwloaded etc. | Verify the event logs for GitHub connector for different types of event like login, logout, file_downloaded etc. | 1 | Event logs for different types of event like login, logout, APiTotalUsage etc. | Event logs of GitHub connector should be correct |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
AWS_GitHub_UI_025 | AWS-GitHub-TC-030 | Verify logs are being ingested correctly in the respective destination and types | Verify logs are being ingested correctly in the respective destination and types through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on ingestion | User should be able to navigate to ingestions
|  |  |  | 3 | Click on Add destination for for audit logs igestion and also add format | User should be able to add Destination for ingestions to store audit logs.
|  |  |  | 4 | Go to the destination and verify logs and format | Logs should ingest to the correct path with selected schema and format.
AWS_GitHub_UI_026 | AWS-GitHub-TC-031 | Verify that user should be able to configure more than one GitHub connector | Verify that user should be able to configure more than one GitHub connector through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on Create App Authorization and create mulitple app authorization for GitHub app | User should be able to create multiple app authorization for GitHub app.
AWS_GitHub_UI_027 | AWS-GitHub-TC-032 | Verify that user should be able to see the connection details for GitHub connector | Verify that user should be able to see the connection details for GitHub connector through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created 4. Ingestion should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Verify the details of GitHub app | User should be able to verify the details of GitHub app.
AWS_GitHub_UI_031 | AWS-GitHub-TC-033 | Verify that user should be able to perform user access for multiple ISV | Verify that user should be able to perform user access for multiple ISV through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created 3. App Authorization should be created for multiple ISV | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Positive | No | [6 empty] | UI Test Case
|  |  |  | 2 | Create App authorization for multiple ISV | User should be able to create app authorization for multiple ISV.
|  |  |  | 3 | Verify User access | User should get details of app authorization for multiple ISV
AWS-GitHub_UI-032 | AWS-GitHub-TC-034 | Verify pagination for GitHub audit logs through UI | Verify pagination for GitHub audit logs through UI | 1 | Generate audit logs for more than 100 records | Audit log should be generated | Multiple audit log files generated with each file having maximum of 16 records | Pass
Negative Scenario
AWS_GitHub_UI_028 | AWS-GitHub-TC-036 | Verify that user should get valid error message for invalid value of encryption type while creating bundle | Verify that user should get valid error message for invalid value of encryption type while creating bundle. Pre Condition: 1. User should have aws credentials | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Can't be tested |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to click on App Bundle
|  |  |  | 3 | Provide invalid value to encryption type and click on submit | User should get valid error message for invalid value of encryption type | We dont have option to give Invalid and Empty Value for Encryption Type
AWS_GitHub_UI_028 | AWS-GitHub-TC-037 | Verify that user should get valid error message for empty value of encryption type while creating bundle | Verify that user should get valid error message for empty value of encryption type while creating bundle. Pre Condition: 1. User should have aws credentials | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Can't be tested |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Bundle | User should be able to click on App Bundle
|  |  |  | 3 | Provide empty value to encryption type and click on submit | User should get valid error message for empty value of encryption type | We dont have option to give Invalid and Empty Value for Encryption Type
AWS_GitHub_UI_029 | AWS-GitHub-TC-038 | Verify that user should get valid error message for invalid value of client id | Verify that user should get valid error message for invalid value of client id through AppFabric UI. Pre Condition: Login to Amazon AWS AppFabric account. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client id and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of client id | User should get valid error message
AWS_GitHub_UI_029 | AWS-GitHub-TC-039 | Verify that user should get valid error message for empty value of client id | Verify that user should get valid error message for empty value of client id through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client id and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of client id | User should get valid error message
AWS_GitHub_UI_030 | AWS-GitHub-TC-040 | Verify that user should get valid error message for invalid value of client secret | Verify that user should get valid error message for invalid value of client secret through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client secret and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of client secret | User should get valid error message
AWS_GitHub_UI_030 | AWS-GitHub-TC-041 | Verify that user should get valid error message for empty value of client secret | Verify that user should get valid error message for empty value of client secret through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of client secret and secret, Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of client secret | User should get valid error message
AWS_GitHub_UI_031 | AWS-GitHub-TC-042 | Verify that user should get valid error message for invalid value of tenant id | Verify that user should get valid error message for invalid value of tenant id through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of tenant id , Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of tenant id | User should get valid error message
AWS_GitHub_UI_031 | AWS-GitHub-TC-043 | Verify that user should get valid error message for empty value of tenant id | Verify that user should get valid error message for empty value of tenant id through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass (App Auth is successful with invalid value of tenant id , Ingestion fails) |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of tenant id | User should get valid error message
AWS_GitHub_UI_032 | AWS-GitHub-TC-044 | Verify that user should get valid error message for invalid value of tenant name | Verify that user should get valid error message for invalid value of tenant name through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric | We can give any value to tenant name. So can't test this for invalid value of tenant name | Can't be tested |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of tenant name | User should get valid error message
AWS_GitHub_UI_032 | AWS-GitHub-TC-045 | Verify that user should get valid error message for empty value of tenant name | Verify that user should get valid error message for empty value of tenant name through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of tenant name | User should get valid error message
AWS_GitHub_UI_033 | AWS-GitHub-TC-046 | Verify that user should get valid error message for invalid value of Amazon S3 path. | Verify that user should get valid error message for invalid value of Amazon S3 path through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide invalid value of Amazon S3 path | User should get valid error message
AWS_GitHub_UI_034 | AWS-GitHub-TC-047 | Verify that user should get valid error message for empty value of destination | Verify that user should get valid error message for empty value of destination through AppFabric UI. Pre Condition: 1. Login to Amazon AWS AppFabric Account. 2. AppBundle Should be created | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Click on create app authorization and provide empty value of destination | User should get valid error message
AWS_GitHub_UI_035 | AWS-GitHub-TC-048 | Verify that user should get valid error message for invalid value of user email address for user access | Verify that user should get valid error message for invalid value of user email address for user access through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on user access | User should be able to navigate to user access
|  |  |  | 3 | Provide invalid email address | User should get valid error message
AWS_GitHub_UI_036 | AWS-GitHub-TC-049 | Verify that user should get valid error message if user does not have permission for the action | Verify that user should get valid error message if user does not have permission for the action through AppFabric UI. | 1 | Login to AWS app fabric with user having less permission | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Try to perform any action which does not have access to the user | User should get valid error message
AWS_GitHub_UI_037 | AWS-GitHub-TC-050 | Verify that user should get valid error message for ingestion if client secret is expired after app authorization. | Verify that user should get valid error message for ingestion if client secret is expired after app authorization through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Token not expiring for Github Oauth apps |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Create App Authorization by providing valid client secret | User should be able to create app authorization for GitHub app.
|  |  |  | 4 | After client secret expiration, try to create another app authorization for GitHub app. | User should get valid error message
AWS_GitHub_UI_038 | AWS-GitHub-TC-051 | Verify that user should get valid error message for ingestion if password is changed after app authorization. | Verify that user should get valid error message for ingestion if password is changed after app authorization. through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Create App Authorization by providing valid client secret | User should be able to create app authorization for GitHub app.
|  |  |  | 4 | After client secret expiration, try to create another app authorization for GitHub app. | User should get valid error message
AWS_GitHub_UI_039 | AWS-GitHub-TC-052 | Verify that user should get valid error message for invalid value of instance url | Verify that user should get valid error message for invalid value of instance url through AppFabric UI. | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations
|  |  |  | 3 | Connect to GitHub app by providing invalid value of instance URL. | User should get valid error message
AWS_GitHub_UI_040 | AWS-GitHub-TC-052 | Verify that user should get valid error message for creating ingestion if app is not connected. | Verify that user should get valid error message for creating ingestion if app is not connected through App Fabric UI | 1 | Go to "AWS AppFabric". | User should be able to navigate to Aws AppFabric |  | Pass |  | P1 | Negative | No | [6 empty] | UI Test Case
|  |  |  | 2 | Click on App Authorization | User should be able to navigate to App Authorizations and authorize GitHub app.
|  |  |  | 3 | Create ingestion without connecting to the app | User should get valid error message.

## SIM_ISSUES
SIM number | Issue Summary | Status
P102948176 | Github: Trying to create app authorization for Github through Console for NRT region. Getting error: oauth2 app authorization configuration is not valid | Resolved
P102834609 | Github: Audit logs file does not contain User Email | Resolved
P103053197 | Github: Fabric events are not getting populated under event_code in audit log file | Resolved
P102683798 | GitHub: Getting Internal Server error in GetUser API response for Github | Resolved
P102485455 | Github: Trying to create app authorization for Github through Console. Getting error: oauth2 app authorization configuration is not valid | Resolved
P102605134 | Github: Audit logs file not generated after Create Ingestion from UI | Resolved
P102485468 | GiHub: Trying to connect app authorization for Github through API.Getting error: The application error is: {\"error\":\"Not Found\"} | Resolved
P102683679 | GitHub: Audit logs are getting empty in GetAuditLog API response | Resolved
P103183644 | Github: Events in the events dictionary file are not coming in the audit logs as those are Security events | Open

## AuditLog_eventTesting
AppFabric event types need testing | Corresponding events from Github | Status
workspace_user_added | org.invite_member,org.add_member | Pass
entity_created | repo.create, organization_default_label.create | Pass
workspace_configuration_activity | repository_vulnerability_alerts.disable | Pass
group_user_added | team.add_member | Pass
workspace_user_updated | org.update_member | Pass
group_updated | team.add_repository | Pass
group_user_deleted | team.remove_member | Pass
entity_deleted | oauth_access.destroy | Pass
permission_updated | environment.update_actions_secret | Pass
file_downloaded | repo.download_zip | Pass
user_created | "user.create" | Not coming in github Audit logs
user_enabled | NA | Not present in Github events dictionary
user_password_changed | "user.change_password": | Not coming in github Audit logs
user_password_reset | "user.forgot_password": | Not coming in github Audit logs
user_unlocked | NA | Not present in Github events dictionary
user_role_added | NA | Not present in Github events dictionary
user_role_updated | NA | Not present in Github events dictionary
user_role_deleted | NA | Not present in Github events dictionary
group_role_created | NA | Not present in Github events dictionary
group_role_deleted | NA | Not present in Github events dictionary
group_role_updated | "team.change_privacy" | Pass
group_membership_updated | NA | Not present in Github events dictionary
user_login | "user.login" | Not coming in github Audit logs
user_logoff | NA | Not present in Github events dictionary
user_login_failed | "user.failed_login" | Not coming in github Audit logs
file_downloaded | "repo.download_zip": | Pass
file_exported | "org.audit_log_export" | This event is not getting created in Audit logs even after performing the action for exporting audit logs

## Integration_testing_BetaReports
Integration test report for Github
https://tod.amazon.com/test_runs/699343788585-45027b6b243b5827098d93ee8697a436-90c8433a-SJBI0wfaaf-1697707684
Integration test screenshot for Github